## Reporting Framework
QA REPORTING FRAMEWORK - Reports, Frequency and Metrics published in each sprint phase
Timeline | Week1 | Week2 - Week3 | Week4 - Week5 (Till Go-Live) | Published On | Sender | Recipient
Sprint Phases | Req. & Design | Dev & QA | Regression & UAT
DAILY QA STATUS REPORT | Daily Sprint Summary | Sprint Summary | Sprint Summary | Mon, Wed, Thu (Before 7.00pm) | QA Leads (Juthika / Ranjana) | Engineering Team, Tech Managers, Madhu, Manmeet
| Testcase Design | Testcase Design | Testcase Design
|  | New Feature Testcase Execution | New Feature Testcase Execution
|  | Bug Report - Status Wise | Bug Report - Status Wise
|  | Bug Report - Severity & Priority Wise | Bug Report - Severity & Priority Wise
Regression Testing - Risk Overview
Test Automation Report
WEEKLY QA BUILD ACCEPTANCE REPORT |  | Testcase Design Overview - DEV TCs | Testcase Design Overview - DEV TCs | Tue (Before 7.00pm) | Test Manager (Ayub) | Engineering Team, Tech Managers, Design Councel Madhu, Manmeet
|  | Bug Report - Level Wise (Known Issues) | Bug Report - Level Wise (Known Issues)
|  | QA Sanity Testcase Execution | QA Sanity Testcase Execution
WEEKLY QA STATUS REPORT | Weekly Sprint Summary | Weekly Sprint Summary | Weekly Sprint Summary | Fri (Before 7.00pm) | Test Manager (Ayub) | Engineering Team, Tech Managers, Design Councel Madhu, Manmeet
| Weekly Sprint Status Tracker | Weekly Sprint Status Tracker | Weekly Sprint Status Tracker
| Testcase Design Overview | Testcase Design Overview | Testcase Design Overview
|  | Sanity Testcase Execution | Sanity Testcase Execution
|  | New Feature Testcase Execution | New Feature Testcase Execution
|  | Testcase Execution - Component Wise | Testcase Execution - Component Wise
|  | Bug Report - Status Wise | Bug Report - Status Wise
|  | Bug Report - Severity & Priority Wise | Bug Report - Severity & Priority Wise
|  | Bug Report - Component Wise | Bug Report - Component Wise
|  | Bug Report - Component Wise - P1 | Bug Report - Component Wise - P1
|  | Bug Report - Level Wise ( Known Issues) | Bug Report - Level Wise ( Known Issues)
Regression Testing - Risk Overview
Test Automation Report
SPRINT SUMMARY REPORT |  |  | Sprint Summary | Day After Go-Live (Before 7.00pm) | Test Manager (Ayub) | Engineering Team, Tech Managers, Design Councel Madhu, Manmeet , Implementation Team, Initiatives, EkStep Leadership
Sprint Status Tracker
Risk Summary - Regression Test Coverage
Testcase Design Coverage - Component Wise
Test execution Coverage - Component Wise
Test Automation Coverage
Bug Report - Status Wise
Bug Report - Severity & Priority Wise
Bug Report - Component Wise
Bug Report - Component Wise - P1
Bug Report - Level Wise ( Known Issues)
Recommendations & Lessons Learnt

## Weekly Status 1
Sprint Weekly Status Tracker
Sunbird Sprint Phases | 2018-04-30 | 2018-05-07 | 2018-05-01 | 2018-05-08 | 2018-05-15 | 2018-05-22 | 2018-05-29 | 2018-06-05 | 2018-06-12 | 2018-06-19 | 2018-06-26 | 2018-07-03 | 2018-07-10 | 2018-07-17 | 2018-07-24 | 2018-07-31 | Remarks
Requirement Freeze
Dev Test Case Design Sign off
QA Test Case Design Sign off
Weekly Deployment Post Completion of Dev TC Execution
Acceptance of Dev Build by QA for Testing Post Completion of QA Sanity Testing
Completion of QA Functional Test Case Execution
Completion of QA API Testing
Completion of QA Regression Testing
QA Test Automation Scripting Sign off
Completion of Automated Testing
UAT Test Sign off
Go-Live
Mobile App Sprint Phases
Requirement Freeze
Dev Test Case Design Sign off
QA Test Case Design Sign off
Weekly Deployment Post Completion of Dev TC Execution
Acceptance of Dev Build by QA for Testing Post Completion of QA Sanity Testing
Completion of QA Functional Test Case Execution
Completion of QA API Testing
Completion of QA Regression Testing
QA Test Automation Scripting Sign off
Completion of Automated Testing
UAT Test Sign off
Go-Live
Legend | Delayed |  |  |  |  | R
| Progressing with Delay |  |  |  |  | A
| On Track |  |  |  |  | G
| Not Applicable |  |  |  |  | NA

## Weekly Status 2
Project Weekly Status Tracker
Completed QA Activities – This Week
1 | QA has completed Release 1.6.0 on time and there were no production issues raised till date
2 | Ionic App was tested and released to Diksha on time
3 | Designing test cases for new features (JIRA IDs)
Planned QA Activities – Next Week
1 | Execution of new feature test cases (Week1)
Key Highlights
1 | Release 1.6.0 is completed and moved to Production
2 | Ionic App was tested and released to Diksha on time
Challenges Encountered and Possible Resolutions
| Challenges | Resolutions
1 | There were 10+ S1's raised during the first day of testing, because of which QA has rejected Release 1.7.0 build | PM's to Provide KT on new features and spend some time with QA on reviewing the test cases
2 | Requirements are not clearly documented nor any KT were provided for new features

## Test Design
Manual Testcase Design Overview
Sunbird Release 1.7.0
|  |  | Dev Test Case Design |  | QA Test Case Design
S. No. | Component / Module | Description | # TC Designed | Review Status (By QA) | # TC Designed | Review Status (By PM) | Remarks
1 |  | Data generation for consumption APIs testing | 12 | Completed | 43 | Completed
2 |  | Description2 | 13 | Completed | 44 | Completed
3 |  | Description3 | NA | NA | 25 | NA
4 |  | Description4 | 15 | Completed | 46 | Delayed
5 |  | Description5 | 15 | In Progress | 46 | In Progress
6 |  | Description6 | 15 | In Progress | 46 | In Progress
7 |  | Description7 | 15 | In Progress | 46 | In Progress
8 |  | Description8 | 15 | In Progress | 46 | In Progress
9 |  | Description9 | 15 | In Progress | 46 | In Progress
10 |  | Description10 | 15 | In Progress | 46 | In Progress
11 |  | Description11 | 15 | In Progress | 46 | In Progress
12 |  | Description12 | 15 | In Progress | 46 | In Progress
13 |  | Description13 | 15 | In Progress | 46 | In Progress
14 |  | Description14 | 15 | In Progress | 46 | In Progress
15 |  | Description15 | 15 | In Progress | 46 | In Progress
16 |  | Description16 | 15 | In Progress | 46 | In Progress

## Bug Reports
Daily Bug Progress Report
Daily Bug Logged Status | 2019-02-13 | 2019-02-14 | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | 2019-03-04
Open
In Progress
Resolved
Re Open
Closed
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bug Snapshot | Blocker/critical | Major | Minor/ Trivial
Open | 5 | 10 | 15
In Progress | 4 | 2 | 3
Resolved | 6 | 3 | 4
Re Open | 2 | 1 | 4
Closed | 4 | 3 | 2
S1 Total | 21 | 19 | 28
P1 Bug Snapshot | P1 | P2 | P3
Open | 3 | 12 | 15
In Progress | 3 | 3 | 3
Resolved | 2 | 5 | 6
Re Open | 2 | 1 | 4
Closed | 2 | 5 | 2
P1 Total | 12 | 26 | 30
Component wise Bug Status
Component / Module wise Bugs | Open | In Progress | Resolved | Re Open | Closed | Known Issue to remain Open for Next Level |  | Open / In Progress / Re Open P1
Announcement | 2 | 2 | 2 | 2 | 2 | 2 |  | 2
Workspace | 3 | 4 | 3 | 3 | 3 | 3 |  | 1
Library | 6 | 6 | 6 | 6 | 6 | 6 |  | 4
Community | 2 | 2 | 2 | 2 | 8 | 5 |  | 0
Profile | 4 | 8 | 8 | 5 | 9 | 4 |  | 0
Login | 1 | 0 | 1 | 1 | 6 | 1 |  | 0
Course | 2 | 0 | 5 | 5 | 2 | 5 |  | 0
Admin | 0 | 7 | 3 | 5 | 0 | 5 |  | 0
Collection Editor | 0 | 8 | 3 | 0 | 0 | 0 |  | 0
APIs | 2 | 2 | 2 | 2 | 5 | 5 |  | 1
Component 11 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Component 12 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Team wise Bug Status
Bug Logged By | Total | Open | In Progress | Resolved | Reopen | Closed | Known Issue to remain Open for Next Level | Description of Known Issues
Dev Issues | 120 | 5 | 5 | 100 | 8 | 100 | 28
QA Issues | 250 | 55 | 20 | 180 | 40 | 180 | 90
Field Issues | 7 | 4 | 4 | 7 | 0 | 7 | 0
User Issues | 22 | 2 | 5 | 0 | 5 | 3 | 0

## Test Execution
Release/ Build No: Production Android App 1.23
Overall Status: Completed
Test Case Execution - 14/02/2019
| Application | Total TC Count | Executed | Passed | Failed | Blocked | % Passed | % Completed
| Shop Ammoun | 66 | 66 | 55 | 11 | 0 | 83.33% | 100%
New Feature Testing Status:
| Application | Total TC Count | Executed | Passed | Failed | Blocked | % Passed | % Completed
| Sunbird | 500 | 200 | 150 | 30 | 20 | 30% | 40%
API
Mobile App
Risks/ Mitigation:
QA Testcases Count Overview
S. No. | Planned Req. ID | Component / Module | Description | # Designed | # Executed | # Passed | # Failed | # Blocked | % Completed
1 | SB3487 |  | Data generation for consumption APIs testing | 43 | 43 | 39 | 1 | 3 | 100%
2 | SB3488 |  | Description2 | 44 | 44 | 44 | 0 | 0 | 100%
3 | SB3489 |  | Description3 | 20 | 10 | 6 | 0 | 4 | 50%
4 | SB3490 |  | Description4 | 46 | 0 | 0 | 0 | 0 | 0%
5 | SB3491 |  | Description5 | 46
6 | SB3492 |  | Description6 | 46
7 | SB3493 |  | Description7 | 46
8 | SB3494 |  | Description8 | 46
9 | SB3495 |  | Description9 | 46
10 | SB3496 |  | Description10 | 46
11 | SB3497 |  | Description11 | 46
12 | SB3498 |  | Description12 | 46
13 | SB3499 |  | Description13 | 46
14 | SB3500 |  | Description14 | 46
15 | SB3501 |  | Description15 | 46
16 | SB3502 |  | Description16 | 46

## Sheet1
Critical | 8
Major | 18
Minor | 17

## Regression Overview
Regression Overview
Sl. No | Component / Module | Sub Modules | Regression TC Count | Executed | Failed | Regression Bugs (Open / In Progress / Re Open) | Functional Bugs (Open / In Progress / Re Open) | Status | Re-testing Required | Project Risk Remarks
1 | Sanity Scenarios |  | 55 | 55 | 0 | 0 | 0 | Completed | No | Working as Expected
2 | Announcement | Creation | 51 | 51 | 8 | 0 | 4 | Incomplete | Yes | As the basic flow is not working, Need to rerun the test cases post new build
|  | Consumption | 17 | 10 | 0 | 0 | 5 | In Progress
|  | Announcement Dashboard | NA |  |  | 0 | 2
3 | Workspace | Book | 4 |  |  | 0 | 1
|  | Course | 5 |  |  | 0 | 1
|  | Collection | 4 |  |  | 0
|  | Lesson Plan | 4 |  |  | 0
|  | Resource | 4 |  |  | 0
|  | Uploads | 16 |  |  | 0
|  | External URL | 15 |  |  | 0
|  | Content Curation/Reviewer procress | 11 |  |  | 0
|  | User wise option availability | 11 |  |  | 0
|  | Content Flagging flow | 40 |  |  | 0
|  | Limited Listing | 25 |  |  | 0
4 | Library | All | 25
|  | Copy Content | 18
5 | Community | NA | 79
6 | Profile |  | 60
7 | Login | Login | 24
|  | New Password on first login | 3
|  | Welcome sms | 4
|  | Session Timeout | 2
|  | Forgot Password | 7
|  | Login with username/mail ID/phone number | 3
|  | User phone number change | 5
|  | Forgot password with phone number | 7
8 | Course | Batch Creation | 10
|  | Batch updation | 14
|  | Course Creator Dashboard | 4
|  | Course Mentor Dashboard | 5
9 | Admin | Org Management | 6
|  | User Management | 12
|  | Admin dashboard | 11
|  | Org Type set up | 3
|  | "President Gold Medal" badge to Teacher's profile | 3
|  | User and Org search on profile | 8
10 | Collection Editor |  | 213
11 | APIs |  | 50
| Total |  | 783

## Automation Status
S. No. | Component/ Module | Sub Module | # Total TCs | # TCs Automated | % Automation Completed | Automation Scripts Last Run Date | Target Automation % | Test Execution Effort (Man-Hrs) for Automated Tests when done completely manually per cycle | Remarks
1 | Sanity Testing |  | 55 |  |  |  |  | 67.9167
2 | Regression Testing
| Announcement | Creation | 51 |  |  |  |  | #REF!
|  | Consumption | 17 |  |  |  |  | #REF!
|  | Announcement Dashboard | NA
| Workspace | Book | 4
|  | Course | 5
|  | Collection | 4
|  | Lesson Plan | 4
|  | Resource | 4
|  | Uploads | 16
|  | External URL | 15
|  | Content Curation/Reviewer procress | 11
|  | User wise option availability | 11
|  | Content Flagging flow | 40
|  | Limited Listing | 25
| Library | All | 25
|  | Copy Content | 18
| Community | NA | 79
| Profile |  | 60
| Login | Login | 24
|  | New Password on first login | 3
|  | Welcome sms | 4
|  | Session Timeout | 2
|  | Forgot Password | 7
|  | Login with username/mail ID/phone number | 3
|  | User phone number change | 5
|  | Forgot password with phone number | 7
| Course | Batch Creation | 10
|  | Batch updation | 14
|  | Course Creator Dashboard | 4
|  | Course Mentor Dashboard | 5
| Admin | Org Management | 6
|  | User Management | 12
|  | Admin dashboard | 11
|  | Org Type set up | 3
|  | "President Gold Medal" badge to Teacher's profile | 3
|  | User and Org search on profile | 8
| Collection Editor |  | 213
3 | APIs Automation |  | 50
| Total |  | 783